## Sheet1
Risk ID | Risk Description | Likelihood | Impact | Risk Score | Mitigation Strategy | Team | Status
1 | Delays in development due to lack of resources | High | High | 9 | Hire additional developers | Harshdeep Singh | Open
2 | Data security breach | Medium | High | 6 | Implement stricter security measures | Harshdeep Singh | Open
3 | Technical debt accumulation leading to performance issues | Medium | Medium | 4 | Regular code reviews and refactoring | Nirmal Kaur | Open
4 | Lack of user adoption due to poor UI design | Low | Medium | 2 | Conduct user testing before release | Harshdeep Singh | Open
5 | Budget overrun | Medium | High | 6 | Monitor expenses closely | Prabhjot Kaur | Open
6 | Incorrect or incomplete requirements leading to rework | High | High | 9 | Thorough requirements gathering and validation | Nirmal Kaur | Open
7 | System outages during peak traffic times | Medium | High | 6 | Implement load balancing and failover systems | Nirmal Kaur | Open
8 | Insufficient testing leading to bugs in production | Medium | High | 6 | Increase test coverage and automate tests | Prabhjot Kaur | Open
9 | Legal compliance issues | Low | High | 3 | Work closely with legal team to ensure compliance | Prabhjot Kaur | Open
10 | Stakeholder changes mid-project | High | Medium | 6 | Establish clear communication with stakeholders | Harshdeep Singh | Open